## Sheet1
Issue ID | Description | Action
1 | Existing Arduino hardware available for the project doesn't have ethernet or WiFi network connectivity | Purchase ESP8266 ethernet module
2 | Only one set of hardware (Arduino etc) makes it difficult for multiple group members to test code | Assignment roles put in place, hardware and coding to GD, other tasks split across the team to even the workload
3 | Finding a time to meet as a group is proving very difficult | Make do with using chat groups in MS Teams
4 | Temperature and humidity sensor fried due to reverse polatiry power connection. No duplicate replacement sensor available for prototype and local stores like Jaycar are too expensive, not enough time to order online and have affordable replacement shipped | Use digital or analogue temperature sensor instead. Prototype will go without a humiditiy sensor
5 | Blynk doesn't work well with the delay() function, however using the BlynkTimer or SimpleTimer functions requires more intermediate Arduino prgramming knowledge | The prototype will not have a combined sketch, this will need to be compelted in the next phase
6 | Using ESP8266 with AT firmware as a modem for the Arduino board is a big learning curve, not recommended for beginners. GD unable to get the NTP feature completed as planned as part of the prototype functionality | Push development of NTP connection out past the assignment due date into the future plan
7 | Finding it difficult to get multiple pieces of code from various standalone & functioning sketches combined into a single functioning sketch | The prototype will not have a combined sketch, this will need to be compelted in the next phase
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27